## Action Plan 2019-23
SCTS Equalities Outcomes Action Plan for 2019-23
Equality Outcome | Supporting Outcomes | Actions |  |  |  | Progress | Protected Characteristic Supported
|  | Description | By When | Status | Lead |  | Sex | Disability | Race | SO | R&B | P,M,& B | GR | M or CP | Age
1. We will promote awareness and understanding of equality and diversity within our organisation by: | • promoting the value of submitting and collecting appropriate equality monitoring data; | In order to be able to accurately report on equality, diversity and inclusion, to mainstream equality and to be able to offer appropriate support to members of staff it is crucial to be able to collect accurate data. There are three steps that are necessary in this process: |  |  |  |  | x | x | x | x | x | x | x | x | x
|  | • a set of new monitoring questions and answers has to be agreed and consulted with the Equality Advisory Group, the Public and Commercial Services union (PCS) and all other relevant organisations; |  | COMPLETED | HRU E&D Manager | March 2019 - The exercise of mapping all questions currently available in all HR systems was conducted by the HRU and E&D Manager. The SCTS Equality Advisory Group and PCS were also consulted about the questions. A set of new questions that will be used across all HR systems has been agreed.
|  | • all HR systems require to be amended - EROL, HR Connect & Resourcelink - and when a new unified HR system is introduced the same questions will be used; | 2019-05-01 | ON TRACK | HRU | March 2019 - The Equality Monitoring questions on the recruitment system (EROL) have been updated to reflect the new wording agreed and this will go live at the start of April 2019. HR Connect (Resourcelink) wording has been agreed however there is more work to do to ensure that no data is lost when wording is updated and that we are still able to meet reporting requirements if we change the categories of data. This work will be completed by the end May 2019.
|  | • a campaign for staff promoting the value of submitting data on protected characteristics will be launched - it will involve a case study of situations when adjustments have been put in place as a result of providing information about particular protected characteristics. | 2019-10-01 | ON TRACK | HRU E&D Manager | March 2019 - The E&D Manager, in preparation for this task, has been working with a number of organisations that have successfully introduced such campaigns, so the SCTS can apply lessons learned elsewhere. The campaign will be launched after the HR systems have been amended.
| • introducing Inclusion Ambassadors with specialist knowledge of the protected characteristics; | We will appoint members of staff to act as 'ambassadors' for particular protected characteristics, or other community groups, who are willing to be involved in examining matters at a strategic level and working to ensure that our workplace accurately represents the diverse communities that we serve and to assist in the delivery of our commitments under the Equality Act. | 2019-11-01 | ON TRACK | E&D Manager HRU | March 2019 - An opportunity to join the scheme has been advertised to the members of the Staff Equality Engagement Network. In May this will be opened up to all staff members. | x | x | x | x | x | x | x | x | x
| • supporting and developing the function of the SCTS Staff Equality Engagement Network (SEEN); | In 2014 a Protected Characteristics Staff Group (PCSG) was established by amalgamating the then Staff Disability Group and LGBT Staff Network. The PCSG was created to advise the SCTS and members of staff about Equality and Inclusion matters, and issues concerning staff and court users with protected characteristics. In 2017 the Group was re-branded as the SCTS Staff Equality Engagement Network (SEEN). The membership is open to all members of staff who have an interest in Equality, Diversity and Inclusion and would like to contribute to our efforts to make the SCTS an even more inclusive place to work. PCS Union is represented on this Group as well. The network intends to increase its membership, so there is at least one member from each business area, as that would enable some of the equality work to be cascaded down to local areas. Until the expansion is completed there is still a need for strong support from the E&D Manager. | ONGOING | ONGOING | E&D Manager | March 2019 - In December 2018 it was decided to move the SEEN network to operate virtually via the Equality Hub on the Intranet and a dedicated mailbox SEEN@scotcourts.gov.uk with only an annual meeting being held face to face. In order to make the staff involvement more manageable, and to enable them to play to their strengths, the members were asked to identify one objective for the year. This could be a one-off activity like organisation of an event during one of the awareness days, or a longer term objective like becoming an 'ambassador' for a particular protected characteristic. In February 2019 members of the SEEN organised two significant events. Equali-Tea on Purple Friday in Aberdeen SC raised £180 for Stonewall UK to help in their fight against discrimination towards LGBT+ people in the UK. In Glasgow SC staff were encouraged to sign the #NoBystanders pledge to show their support to stand up to hateful language and abuse both at work and in the community and support everyone who may experience bullying or harassment because of their protected characteristics (no matter what those may be). | x | x | x | x | x | x | x | x | x
| • offering awareness sessions for members of our staff and introducing bespoke e-learning; | Raising awareness among staff about various aspects of equality, diversity and inclusion is crucial for changing culture and addressing stigma. When the level of awareness is high it is easier to start to focus on peoples' abilities and not their disabilities, which is the overall aim of our work in this area. | ONGOING | ONGOING | E&D Manager ELU HRU | March 2019 - A number of events were organised in 2018 by the E&D Manager e.g. British Sign Language Awareness for Public Bodies training sessions conducted by Deaf Action, a presentation about equality and Diversity delivered by the E&D Manager to Justices of the Peace for Lothian and Borders, a session conducted by R.E.A.C.H. for Autism in Falkirk SC - please see outcome 3 for further details. | x | x | x | x | x | x | x | x | x
| • introducing a Reverse Mentoring scheme. | The aim of this programme is to to assure that there is no discrepancy between visibility and lived experience in the organisation. The mentoring programme will last four sessions over four months, the mentoring agreement will be signed and this outlines what both the mentor and the mentee will agree to during the relationship. The aim is for the junior member of staff (the mentor) to share their experience of living and working with a particular protected characteristic and give further information to improve the senior member of staff’s (the mentee) knowledge of this matter. The mentee will share the knowledge they have gained with their colleagues to raise awareness among other members of staff and to promote an inclusive working environment. The mentee will also offer advice to the mentor about career progression in the organisation or any other matter that would be beneficial for their development. | 2019-11-01 | ON TRACK | E&D Manager ELU HRU | March 2019 - The opportunity to join the scheme has been advertised to the members of the Staff Equality Engagement Network. In May this will be opened up to all staff members. | x | x | x | x | x | x | x | x | x
2. We will improve the accessibility of our services by: | • creating a bespoke page on our website that deals entirely with accessibility information and guidance; | The accessibility website will provide easy access to the following: • videos introducing the court environment and special measures with BSL interpretation, audio and subtitles; • information on how to contact us via contactSCOTLAND-BSL • all existing Easy Read documents; • accessibility audits of SCTS buildings. | 2020-04-01 | ON TRACK | E&D Manager WebTeam | March 2019 - The E&D Manager, in preparation for this task, has been collecting all the content for the website. The work with the WebTeam will start in May. | x | x | x | x | x | x | x | x | x
| • scoping the use of online interpreting and support services at public counters to facilitate ad hoc general enquiries, payment of financial penalties etc.; | Introduction of a pilot scheme for the video remote interpreting (a service that would allow connection with the BSL/English interpreter online) in a few venues and possible installation of the Welcome App (an App that allows people with disabilities to inform the venue about their arrival and what assistance they require) in the same venues as well to evaluate how th two systems work together and affect the accessibility of our services. | 2020-04-01 | ON TRACK | E&D Manage ITU | March 2019 - The E&D Manager has identified two providers of Video Remote Interpreting (VRI) services and has requested the quotes from them. The possibility of using these services with assistance of Unified Comms is also being investigated. A quote for the installation of the Welcome App has been obtained as well. |  | x
| • promoting use of online support services e.g. the Next Generation Text Service, ‘contactSCOTLAND-BSL’ and telephone interpreting, by updating our website pages and raising awareness among members of SCTS staff; | Preparation of a promotional campaign to raise staff awareness of the benefits of using various online support services. | 2019-08-01 | ON TRACK | E&D Manager | March 2019 - • In March 2018 the new telephone interpretetion services provided by Global Connect - the 1st ranked provider under our Framework Agreement contract (SP-16-016) for Interpreting, Translation and Transcription Services - have been launched. • All SCTS venues webpageshave been amended with information about the different forms of assistance with accessibility. Information about contactSCOTLAND-BSL is also provided on the main SCTS website under the tab 'Contact Us'. |  | x
| • implementing recommendations from the Enabling Jury Service Report | The report’s recommendations fall into two categories: those in which procedures can potentially be adapted without changes to legislation and those where it is more likely that new legislation will be required. The second category includes a recommendation that persons other than jury members, for example a BSL/English interpreter or note taker, could be present in the jury room during the jury’s deliberations in the case. Where legislative changes have been proposed in the report these will require to be considered by the Scottish Government and may be subject to wider consultation. | 2021-01-01 | ON TRACK | Development and Innovation | March 2019 - An implementation group has been established to take forward the remaining recommendations of the report with a view to having certain measures - training Jury Liaison Officers for the courts, an online e-learning package for staff, online information sheet for jurors and the purchase of suitable portable equipment - in place by the end of October 2019. |  | x | [6 empty] | x
| • working with other justice agencies to increase the pool of qualified and suitably experienced BSL/English and deaf/blind interpreters working in the justice system; | The SCTS provides BSL/English and deaf/blind interpreters to its service users on the same basis as spoken language interpreters - to the accused in criminal proceedings and to party litigants in civil proceedings. However due to the small pool of BSL/English and deaf/blind interpreters working in the justice system very often there are no interpreters available, which can cause delays and affects the efficiency of our services. | 2019-12-01 | ON TRACK | E&D Manager | March 2019 - • in March 2017 all partners from the justice sector organised an event for BSL/English and deaf/blind interpreters from the whole of Scotland during which the aspect of their work in the justice sector was discussed. The event sought to explain the barriers that prevent interpreters from working in this sector and what would help them to consider applying for justice-related work. The feedback gathered was very useful for justice sector partners to consider in their collaborative work. • a MSc/Postgraduate Diploma in BSL/English Interpreting at Queen Margaret University (QMU) was validated at the end of March 2018 and collaborative work on development of a module on interpreting in justice settings started in October 2018. The E&D Manager has been working closely with QMU, contributing to course content in respect of court proceedings and also on reviewing its final content if required. It is currently planned that the module will be ready for delivery in September 2019. • a bespoke BSL/English and deaf/blind interpretation services framework is being drafted by Police Scotland and the SCTS iwill be a part of this framework. The framework will regulate the provision of interpretation services, and also encourage new interpreters to work in the justice sector. The framework is planned to be ready and fully operating by the end of 2019. • QMU is currently conducting a landscape review of BSL/English and deaf/blind (tactile) interpretation services throughout Scotland. This work reveal which areas of the country are populated by BSL/English interpreters and whether they are willing to work in the justice sector. The final result is supposed to be ready by October 2019. The SCTS will review findings from this report and scope the possibility of conducting a targeted campaign in the areas where there is a shortfall of this type of interpreters. |  | x
3. We will improve accessibility to our employment by: | • engaging with a variety of local communities in order to raise awareness of the critical role the Scottish Courts and Tribunals Service plays in the justice system; | In order to allow the SCTS to be an employer of choice, people need to know the purpose of our organisation and the opportunities of employment in it that are available. It is also important that they are aware how diverse and inclusive an employer the SCTS is and we can do this by promoting our equality, diversity and inclusion work. We can also show the comprehensive package of supporting policies we have e.g. Dignity at Work Policy, Transgender - Transitioning at Work Policy, Equal Opportunities Policy and Shared Parental Leave Policy. | ONGOING | ONGOING | E&D Manager | March 2019 - • the E&D Manager hosted a stand during the last few Doors Open Days in Parliament House in Edinburgh. The stand presented information about our recruitment process, the Modern Apprentice scheme, policies package, values and behaviours etc. The plan is for members of the Staff Equality Engagement Network to host similar stands in their local areas during Doors Open Days events. • the E&D Manager consulted on the SCTS British Sign Language (BSL) Plan during 2018 and as a part of this process communicated with a number of Deaf Clubs around Scotland. A description of the purpose and role of the SCTS was always a part of this communication. • the SCTS has sponsored an award during the Council of Ethnic Minority Voluntary Sector Organisations (CEMVO) Scotland Award Ceremony since 2014. During this year’s award ceremony the SCTS will be promoted on the stage as the diverse and inclusive employer. • the SCTS is one of the cofounders of the Pride in Justice Network, which was established in October 2018 in order to improve inclusivity and to share good practice in supporting LGBT+ communities. The E&D Manager organised the first networking event in Glasgow Sheriff Court that was attended by a number of representatives from both private and public parts of the justice sector. | x | x | x | x | x | x | x | x | x
| • introducing the SCTS Recruitment and Resourcing Strategy with a particular focus on developing SCTS as a socially inclusive employer; | The SCTS recruitment strategy will focus on 4 themes: Clarity, Diversity, Efficiency and Flexibility. The Diversity theme’s focus is “SCTS attracts the broadest range of applicants, is inclusive and draws on all the potential available". The actions will include: • Developing and communicating a strong, distinctive employer brand. • Promoting SCTS as an employer of choice and identifying the best places and ways to advertise our vacancies • Working in partnership with local communities; specialist organisations and academic institutions to develop SCTS as a socially inclusive employer and consider developing “inclusion champions” across SCTS. • When appropriate we will consider using target recruitment campaigns to attract people from under-represented groups. | 2019-08-01 | ON TRACK | HRU (Recruitment Team) E&D Manager | March 2019 - • Workshops were held in August 2018 with key stakeholders from across the business including PCS representatives. • Key themes and measures of success have been drafted: • Clarity – our approach to recruitment is based on a clear understanding of the skills, knowledge and attributes we need to deliver our business now and in the future • Diversity – SCTS attracts the broadest range of applicants and draws on all the potential available • Efficiency – Our recruitment processes and systems are easy to use and fit for purpose • Flexibility – our selection methods are adaptable and our offer to recruits allows everyone to learn, develop and flourish. • A presentation to the People Committee took place on 31 October – the draft strategy is still being worked on and anticipated to be completed during the summer 2019. | x | x | x | x | x | x | x | x | x
| • improving accessibility to the recruitment section of our website; | Our recruitment website and recruitment documents need to be made more accessible. All the information about our recruitment process needs to be in formats that are accessible to individuals with various conditions, disabilities or particular protected characteristics, so they can make a conscious decision whether they are a suitable candidate for a particular position. | 2020-04-01 | ON TRACK | E&D Manager HRU (Recruitment Team) WebTeam | March 2019 - • an amended, more accessible, ‘Role Profile’ document has been created and it will be in use from April 2019; • the equality monitoring questions have been revised and the new set of question will be in use from April 2019; • the contact details for the Recruitment Team have been amended by adding the possibility of contact via contactSCOTLAND-BSL; • we are scoping the possibility of adding subtitles and BSL/English interpretation to our Induction video; • we are planning to create a video about our recruitment process with audio, subtitles and BSL/English interpretation,to assist Deaf/BSL users, deaf people or people with hearing impairment and blind people or people with visual impairments; • we are planning to review the ‘Job Description’ document to make it more accessible and to ensure that inclusive language is used. | x | x | x | x | x | x | x | x | x
| • introducing an inclusive work placement scheme in order to assist people to gain work experience; and in preparation for same to raise associated awareness among members of staff. | By introducing work placements for people with various conditions, disabilities or particular protected characteristics we are supporting communities by offering these people, who are often from deprived areas, a chance to gain experience and familiarity with a workplace environment. This also would allow us to project a positive image of the SCTS as a diverse and inclusive employer. To prepare for specific placements, awareness sessions will be organised for staff members in order to make them focus on an individual’s ability and not disability, condition or particular protected characteristic when the placement starts. | ONGOING | ONGOING | E&D Manager HRU | March 2019 - In 2018 the E&D Manager made arrangements with CashBack for Communities to work with the National Autistic Society’s Moving Forward project. This project is funded by CashBack for Communities and supports young people with autism from disadvantaged areas across West and Central Scotland. Young people begin by attending eight group based training sessions in order to develop social confidence and readiness for employment. Further to this group work, each young person is given an opportunity to undertake a work experience placement with one of the employer partners. Placements are usually part time and last around eight weeks, though the duration can be reduced or increased to suit the needs of the host employer. As well as placements, young people are given support to identify and apply for suitable paid employment. Following a meeting in December 2018 we are now in the process of introducing a pilot of this scheme in Falkirk Sheriff Court. Court staff and CashBack for Communities are working closely together to create the best possible environment for individuals during their placement. In preparation for this scheme a number of steps have also been taken to raise awareness amongst staff about autism e.g. a session was organised at which R.E.A.C.H. for Autism presented a performance of the REACH for Change group’s famous play - ‘In Our World: A Day on the Spectrum’. New scenes were added to better show the experience of a person with autism within a court environment. | x | x | x | x | x | x | x | x | x